## Timeline
# | Activity | Plan |  | Actual |  | Additional Notes
|  | Start | End | Start | Finished
A | Analysis Phase | 2017-09-30 | 2017-10-08 | 2017-09-30
1 | Plan development timeline | 2017-09-30 | 2017-10-02 | 2017-09-30 | 2017-10-03
2 | Collect resources (libraries, articles, etc) | 2017-10-02 | 2017-10-03 | 2017-10-03 | 2017-10-03 | Library chosen: EmguCV (OpenCV wrapper for C# .NET)
3 | Define Requirement Document | 2017-10-04 | 2017-10-06 | 2017-10-04 | 2017-10-06
4 | Define Technical Design Document | 2017-10-06 | 2017-10-08 | 2017-10-06 | 2017-10-15 | Switch Priority to project structure
B | Implementation Phase | 2017-10-08 | 2017-11-04 | 2017-10-06
1 | Create Solution project scratch | 2017-10-08 | 2017-10-08 | 2017-10-06 | 2017-10-06
2 | Prepare development libraries | 2017-10-08 | 2017-10-09 | 2017-10-06 | 2017-10-15 | Stuck on troubleshoot using the library
3 | Implement library sample project | 2017-10-10 | 2017-10-10 | 2017-10-15 | 2017-10-15
| Implement face recognition POC | 2017-10-10 | 2017-10-14
| Implement VPA Face Recognition Module | 2017-10-14 | 2017-10-24
| Implement Form Application for VPA Face Recognition Module | 2017-10-25 | 2017-10-25
| Implement VPA Face Recognition API Module | 2017-10-26 | 2017-10-31
| Tests | 2017-10-31 | 2017-11-02 | 2017-10-15 |  | Start Unit Test after development finished (Each module)
| Deployment | 2017-11-02 | 2017-11-04

## Development Module Breakdown
Module Part | Start | End | Unit Test | Status
Encryption | 2017-10-15 | 2017-10-15 | 2017-10-15 | Passed
I/O Manager | 2017-10-15
Setting Management