## Timeline
# | Activity | Plan |  | Actual |  | Additional Notes
|  | Start | End | Start | Finished
A | Analysis Phase | 2017-09-30 | 2017-10-08 | 2017-09-30
1 | Plan development timeline | 2017-09-30 | 2017-10-02 | 2017-09-30 | 2017-10-03
2 | Collect resources (libraries, articles, etc) | 2017-10-02 | 2017-10-03 | 2017-10-03 | 2017-10-03 | Library chosen: EmguCV (OpenCV wrapper for C# .NET)
3 | Define Requirement Document | 2017-10-04 | 2017-10-06 | 2017-10-04 |  | Currently in Progress
4 | Define Technical Design Document | 2017-10-06 | 2017-10-08
B | Implementation Phase | 2017-10-08 | 2017-11-04
1 | Create Solution project scratch | 2017-10-08 | 2017-10-08
2 | Prepare development libraries | 2017-10-08 | 2017-10-09
3 | Implement library sample project | 2017-10-10 | 2017-10-10
| Implement face recognition POC | 2017-10-10 | 2017-10-14
| Implement VPA Face Recognition Module | 2017-10-14 | 2017-10-24
| Implement Form Application for VPA Face Recognition Module | 2017-10-25 | 2017-10-25
| Implement VPA Face Recognition API Module | 2017-10-26 | 2017-10-31
| Tests | 2017-10-31 | 2017-11-02
| Deployment | 2017-11-02 | 2017-11-04